## Project Schedule
| Work Package | Est.Effort (Man-hour) | Type | Descriptions | Person In Charge | Supporter | Start Time | Deadline | Status | Actual Effort (pds) | Notes
1 | Stage 1 – Kick-off & Scope Definition (04/01/2026 – 18/01/2025)
PROJECT INITIATION AND SCOPE
| Conduct project kick-off workshop, define scope, objectives, roles. | 1 |  | Conduct the initial project kick-off to define high-level scope, objectives, and assign key roles and responsibilities. | All team | ManhNC
| Kick-off Meeting – Exploring and Proposing Project Topics | 5 |  | Initial meeting to brainstorm potential project topics and areas of focus. | All team | ManhNC |  |  | Done
| Meeting with Supervisor – Selecting and Finalizing the Project Topic | 3 |  | Meeting with Supervisor/Mentor to select and formally finalize the project topic for execution. | All team | ManhNC |  |  | Done
| Analyze and validate the selected project topic | 2 |  | Detailed analysis of the chosen topic to understand its constraints and complexity | All team | ManhNC |  |  | Done
| Learn about VinaTech Smart Manufacturing company and business context | 2 |  | Research VinaTech Smart Manufacturing company to understand the business context and industry. | All team | ManhNC |  |  | Done
1.2 | BACKGROUND RESEARCH AND ANALYSIS |  |  |  |  | ManhNC |  |  | Done
| Analyzing the Topic | 3 | Research |  | All team | ManhNC |  |  | Done
| Collect and study template reports | 1 | Research | Collect and study existing report formats to understand reporting requirements and design. | All team | ManhNC |  |  | Done
| Research Product Lines of VinaTech Smart Manufacturing | 1 | Research | Identify and list all product lines, key products, and categories for VinaTech Smart Manufacturing. | All team | ManhNC |  |  | Done
| Study SAP SD Configuration documents | 7 | Research | Study available SAP Materials Management (SD) configuration documents for baseline knowledge. | All team | ManhNC |  |  | Done
| Study SAP MM Configuration documents | 7 | Research | Study available SAP Materials Management (MM) configuration documents for baseline knowledge. | All team | ManhNC |  |  | Done
| Study SAP FI Configuration documents | 7 | Research | Study available SAP Financial Accounting (FI) configuration documents for foundational understanding. | All team | ManhNC |  |  | Done
| Research Config Sale Distribution, Materials Management, Financial Accounting | 3 | Research | Research general configuration best practices for SD, MM and FI in an SAP environment. | All team | ManhNC |  |  | Done
| Research and learn about advanced directions | 4 | Research | Explore advanced directions or latest trends related to the project topic | All team | ManhNC |  |  | Done
| Find out information about VinaTech Smart Manufacturing company | 2 | Research | Find out information about products and prices of VinaTech Smart Manufacturing company | All team | ManhNC |  |  | Done
1.3 | BACKGROUND RESEARCH AND ANALYSIS |  |  |  | All team | ManhNC |  |  | Done
| Prepare Technical Document Template | 2 |  | Prepare a standardized template for technical documentation to be used throughout the project. | All team | ManhNC |  |  | Done
| Draw RACI Matrix | 3 | Design | Draw the RACI matrix to clearly define responsibilities (Responsible, Accountable, Consulted, Informed) for all project tasks. | All team | ManhNC |  |  | Done
| Setup Technical Environment | 1 |  | Set up the necessary technical workspace, tools, and access for the project team. | All team | ManhNC |  |  | Done
| Kick-off Workshop with stakeholders | 4 |  |  | All team | ManhNC |  |  | Done
| Meeting with Supervisor & Mentor – Review documents | 5 |  |  | All team | ManhNC |  |  | Done
| Stage 2 – Requirement Gathering & BRD (18/1/2026 – 24/1/2026) | [7 empty] | Done
2.1 | REQUIREMENTS GATHERING & AS-IS ANALYSIS | [7 empty] | Done
| Collect requirements from stakeholders | 6 | Design | Gather business requirements related to sales order processing, inventory availability, billing, and payment tracking from key users involved in SAP SD, MM, and FI processes. | All team | ManhNC |  |  | Done
| Draw As-Is diagrams | 4 | Design | Document the current order-to-cash process, including Sales Order creation (SD), Goods Issue (MM), Billing and Payment (FI), using AS-IS process flow diagrams. | QuyNT | ManhNC |  |  | Done
| Identify and classify pain points & requirements | 3 | Design | Analyze current issues in order status tracking, inventory synchronization, and billing visibility; classify requirements into mandatory and desired categories. | QuyNT | ManhNC |  |  | Done
| Analyze and validate business data samples | 3 | Design | Review and validate business data samples such as Sales Orders, Material Documents (Goods Issue), and Billing Documents against gathered requirements to ensure feasibility within SAP SD–MM–FI. | QuyNT | ManhNC |  |  | Done
2.2 | TO-BE DESIGN & GAP ANALYSIS | [7 empty] | Done
| Perform Gap-Fit analysis | 4 | Research | Compare AS-IS processes against SAP Standard functionality to identify process and system gaps. | DatNV | ManhNC |  |  | Done
| Define and model TO-BE business processes | 5 | Research | Design and diagram the Future State processes within the SAP system environment. | DatNV | ManhNC |  |  | Done
| Identify RICEFW objects and enhancements | 8 | Research | Determine and list all necessary custom developments (Reports, Interfaces, Conversions, Enhancements, Forms, Workflow) to close identified Gaps. | DatNV | ManhNC |  |  | Done
| Draft preliminary data migration strategy | 3 | Research | Determine initial data entities and outline the basic approach for data migration. | DatNV | ManhNC |  |  | Done
2.3 | DOCUMENTATION AND TECHNICAL PREPARATION | [7 empty] | Done
| Draft complete Business Requirement Document | 5 |  | Consolidate all requirements, AS-IS, TO-BE processes, and Gap Analysis results into the formal BRD. | DucNM | ManhNC |  |  | Done
| Update the scope of work and custom features | 2 |  | Module in scopes MM, FI/CO, Custom Feature: Excel Upload for Goods Receipt | DucNM | ManhNC |  |  | Done
| Develop Functional Specification Documents (FSD) | 6 |  | Write and finalize Functional Specifications for all confirmed custom requirements . | DucNM | ManhNC |  |  | Done
| Align technical architecture & research | 4 |  | Team meeting to finalize technological approach and research necessary technologies for the next stage. | DucNM | ManhNC |  |  | Done
| Complete documents to repository & version control | 2 |  | Save all documents (BRD, FSD, Diagrams, Workflows) to the project repository and ensure proper version control | DucNM | ManhNC |  |  | Done
| Stage 3 –Config (25/1/2026 – 15/2/2026, 20 days) | [7 empty] | Done
3.1 | SALES & INVENTORY BUSINESS PROCESS | [7 empty] | Done
Organization Structure | Company Code | 1 | Master Data | Define company code as the legal entity for accounting and sales transactions | DevTeam | HieuPT |  |  | Done
| Plant | 1 | Master Data | Define plant representing inventory and delivery location | DevTeam | HieuPT |  |  | Done
| Assign Plant to Company Code | 1 | Master Data | Assign plant to controlling company code | DevTeam | HieuPT |  |  | Done
| Storage Locations | 1 | Master Data | Define storage locations for finished goods | DevTeam | HieuPT |  |  | Done
| Maintain Storage Location | 1 | Master Data | Maintain storage location details for inventory tracking | DevTeam | HieuPT |  |  | Done
Sales Order (SD) | Number Range for Sales Order | 1 | Master Data | Define number range interval for sales orders | DevTeam | HieuPT |  |  | Done
| Sales Order Type | 1 | Master Data | Define sales document type for order processing | DevTeam | HieuPT |  |  | Done
| Pricing Procedure | 1 | Standard Config | Configure pricing procedure for sales orders | DevTeam | HieuPT |  |  | Done
| Availability Check (ATP) | 1 | Standard Config | Configure availability check for inventory validation | DevTeam | HieuPT |  |  | Done
| Schedule Line Category | 2 | Standard Config | Define delivery scheduling logic for sales orders | DevTeam | HieuPT |  |  | Done
Goods Issue (MM) | Goods Issue Configuration | 1 | Standard Config | Configure goods issue process for sales order fulfillment | DevTeam | HieuPT |  |  | Done
| Movement Type | 1 | Standard Config | Define movement type for inventory reduction | DevTeam | HieuPT |  |  | Done
| Posting Control |  | Standard Config | Configure inventory and accounting posting during goods issue | DevTeam | HieuPT |  |  | Done
3.2 | FINANCAL PROCESS |  |  |  | DevTeam | HieuPT |  |  | Done
Invoice | Create Billing Document Type | 3 | Standard Config | Define billing document types for customer invoices generated from sales orders | DevTeam | HieuPT |  |  | Done
| Configure Billing Posting | 2 | Standard Config | Configure accounting postings for revenue, tax, and customer receivables | DevTeam | HieuPT |  |  | Done
| Account Determination | 2 | Standard Config | Define G/L account determination for sales revenue and taxes | DevTeam | HieuPT |  |  | Done
Accounts Receivable (Customer) | Customer Account Group | 2 | Standard Config | Define customer account groups for accounts receivable management | DevTeam | HieuPT |  |  | Done
| Payment Terms | 2 | Standard Config | Define payment terms for customer invoices | DevTeam | HieuPT |  |  | Done
| Dunning Procedure | 2 | Standard Config | Configure dunning process for overdue customer invoices | DevTeam | HieuPT |  |  | Done
Payment Processing (Customer) | Manual Customer Payment | 2 | Standard Config | Configure manual payment posting for customer payments | DevTeam | HieuPT |  |  | Done
| Automatic Payment Run | 2 | Standard Config | Configure automatic payment program for customer clearing | DevTeam | HieuPT |  |  | Done
| Clearing Rules | 2 | Standard Config | Configure clearing logic for open customer items | DevTeam | HieuPT |  |  | Done
3.3 | CUSTOMER |  |  |  | DevTeam | HieuPT |  |  | Done
CUSTOMER / BUSINESS PARTNER | Assign Number Range to Customer Account Groups | 2 | Standard Config | Assign number ranges for customer account groups | DevTeam | HieuPT |  |  | Done
| Create Customer Number Ranges | 2 | Standard Config | Define number range intervals for customer master data | DevTeam | HieuPT |  |  | Done
| Define Business Partner Grouping | 2 | Standard Config | Define Business Partner grouping for customer master records | DevTeam | HieuPT |  |  | Done
| Assign BP Roles to Customer Account Groups | 2 | Standard Config | Map Business Partner roles to corresponding customer account groups | DevTeam | HieuPT |  |  | Done
| Stage 4 - Coding & Testing (16/02/2026 – 10/03/2025, 25 days) | [7 empty] | Done
4.1 | W.R.I.C.E.F | [7 empty] | Done
| Reseach & learn BTP,BAS to develop, deploy Fiori application to FLP. | 18 | Research | Focuses on researching and learning SAP Business Technology Platform (BTP) and Business Application Studio (BAS). Request an trial account on SAP BTP for development purpose. Research and practice some projects on BTP. | DevTeam | HieuPT |  |  | Done
| Develop fiori application allow user view order status (R) | 40 | Customize | This application will provide with a portal to view order status. | DevTeam | HieuPT |  |  | Done
4.2 | Document + Testing | [7 empty] | Done
| Develop Functional Specification (FSD) | 5 | Document | Write and finalize Functional Specifications for Order Status Tracking Screen | DevTeam | HieuPT |  |  | Done
| Develop Technical Specification (TSD) | 5 | Document | Write Technical Specification document for Order Status Tracking Screen | DevTeam | HieuPT |  |  | Done
| Develop UM Documents | 10 | Document | Prepare a simplified User Manual to guide users how to system. | DevTeam | HieuPT |  |  | Done
| Test O2C end-to-end | 12 | Test | Perform end-to-end testing of the standard Order-to-Cash process. | DevTeam | HieuPT |  |  | Done
| Test FI posting | 12 | Test | Verify financial integrity by checking whether payment documents generate accurate accounting entries. | DevTeam | HieuPT |  |  | Done
| Test status app | 10 | Test | Test application work correctly with real time data. | DevTeam | HieuPT |  |  | Done
4.3 | Launch Fiori |  |  |  | DevTeam | HieuPT |  |  | Done
| Create CDS View | 5 | Design | [5 empty] | Done
| Publish / Expose OData Service | 5 | Design |  | DevTeam | HieuPT |  |  | Done
| Prepare fiori UI | 10 | Design |  | DevTeam | HieuPT |  |  | Done
| Create Fiori Catalog | 4 | Design |  | DevTeam | HieuPT |  |  | Done
| Create Fiori Group | 2 | Design |  | DevTeam | HieuPT |  |  | Done
| Assign Role | 5 | Design |  | DevTeam | HieuPT |  |  | Done
| Fiori launchpad | 2 | Design |  | DevTeam | HieuPT |  |  | Done
| Stage 5 Document and Overview (11/03/2025 – 18/03/2025, 17 days) | [7 empty] | Done
5.1 | Document | [7 empty] | Done
| Prepare Report 4: Business Blueprint & SDS | 2 |  |  | DucNM | HieuPT |  |  | Done
| Update UC Specification: Goods Issue & Customer Delivery | 2 |  |  | DucNM | HieuPT |  |  | Done
| Prepare Report 5: Test Documentation | 2 |  |  | DucNM | HieuPT |  |  | Done
5.2 | Design | 2 | [6 empty] | Done
| Update SAP Process Flow (Sales Order, Delivery, Goods Issue, Billing) | 2 |  |  | DucNM | HieuPT |  |  | Done
| Update Screen Mock-ups (Fiori: Sales Order Status Tracking) | 2 |  |  | DucNM | HieuPT |  |  | Done
5.3 | Coding/Configuration | [7 empty] | Done
| Configure Standard SAP SD Sales Process (Order-to-Cash) | 2 |  |  | SangNV | HieuPT |  |  | Done
| Develop Sales Order Status Tracking Application | 2 |  |  | SangNV | HieuPT |  |  | Done
| Develop Integration APIs for Delivery and Billing Status | 2 |  |  | SangNV | HieuPT |  |  | Done
| Enhance Control Functions and Frontend (Fiori) | 2 |  |  | SangNV | HieuPT |  |  | Done
| Develop Custom Logs for Sales Order Processing | 2 |  |  | SangNV | HieuPT |  |  | Done
5.4 | Testing | [7 empty] | Done
| Create Sales Order (SO) test data | 2 | Test | Create a sample SO file to generate test data for verifying and validating the ZSDC003 functionality. | SangNV | HieuPT |  |  | Done
| Execute Test Cases (Sales Order, Delivery, Goods Issue, Billing) | 2 |  |  | DatNV | HieuPT |  |  | Done
| Validate Sales Order Status Tracking Function |  |  |  | DucNM | HieuPT |  |  | Done
5.5 | Review & Planning | [7 empty] | Done
| Review Process Flow & Mock-ups | 2 |  |  | ThanhLT | HieuPT |  |  | Done
| Approve Report 4 & 5 | 2 |  |  | ThanhLT | HieuPT |  |  | Done
| Stage 6 – Finalization & Deployment (19/03/2025 – 25/03/2025) | [7 empty] | Done
6.1 | Document | [7 empty] | Done
| Finalize SAP Design Document | 2 |  |  | ThanhLT | HieuPT |  |  | Done
| Finalize Test Documentation | 2 |  |  | ThanhLT | HieuPT |  |  | Done
| Finalize User Guides (Procurement & Finance) | 2 |  |  | ThanhLT | HieuPT |  |  | Done
| Prepare Project Closure Report | 2 |  |  | ThanhLT | HieuPT |  |  | Done
6.2 | Coding | [7 empty] | Done
| Fix Bugs from UAT | 4 |  |  | DevTeam | HieuPT |  |  | Done
| Optimize System Performance | 4 |  |  | DevTeam | HieuPT |  |  | Done
| Finalize Enhancements | 4 |  |  | DevTeam | HieuPT |  |  | Done
6.3 | Testing | [7 empty] | Done
| Final Unit Tests | 2 |  |  | ThanhLT | HieuPT |  |  | Done
| Final Integration Tests (SD–FI) | 2 |  |  | ThanhLT | HieuPT |  |  | Done
| Final Function Tests | 2 |  |  | ThanhLT | HieuPT |  |  | Done
| Bug Fixing & Retesting | 2 |  |  | DevTeam | HieuPT |  |  | Done
6.4 | Deployment | [7 empty] | Done
| Deploy Backend (SAP Core Config + ZTables) | 2 |  |  | QuyNT | HieuPT |  |  | Done
| Deploy Frontend (SAP Fiori Apps) | 2 |  |  | QuyNT | HieuPT |  |  | Done
6.5 | Final Review | [7 empty] | Done
| Final Project Review & Sign-off | 2 |  |  | All team | HieuPT |  |  | Done