## Project Schedule
| Work Package | Est.Effort (Man-hour) | Type | Descriptions | Person In Charge | Supporter | Start Time | Deadline | Status | Actual Effort (pds) | Notes
1 | Stage 1 – Kick-off & Scope Definition (24/09/2025 – 01/10/2025)
PROJECT INITIATION AND SCOPE
| Conduct project kick-off workshop, define scope, objectives, roles. | 1 |  | Conduct the initial project kick-off to define high-level scope, objectives, and assign key roles and responsibilities. | All team
| Kick-off Meeting – Exploring and Proposing Project Topics | 5 |  | Initial meeting to brainstorm potential project topics and areas of focus. | All team |  | 2025-09-24 | 2025-09-24 | Done
| Meeting with Supervisor – Selecting and Finalizing the Project Topic | 3 |  | Meeting with Supervisor/Mentor to select and formally finalize the project topic for execution. | All team |  | 2025-09-24 | 2025-09-25 | Done
| Analyze and validate the selected project topic | 2 |  | Detailed analysis of the chosen topic to understand its constraints and complexity | All team
| Learn about Tecomen company and business context | 2 |  | Research Tecomen company to understand the business context and industry. | All team
1.2 | BACKGROUND RESEARCH AND ANALYSIS
| Analyzing the Topic | 3 | Research |  | All team |  | 2025-09-25 | 2025-09-25 | Done
| Collect and study template reports | 1 | Research | Collect and study existing report formats to understand reporting requirements and design. | TuNT |  | 2025-09-25 | 2025-09-25 | Done
| Research Product Lines of Tecomen | 1 | Research | Identify and list all product lines, key products, and categories for Tecomen. | TuNT |  | 2025-09-25 | 2025-09-25 | Done
| Study SAP MM Configuration documents | 7 | Research | Study available SAP Materials Management (MM) configuration documents for baseline knowledge. | DungNQ |  | 2025-09-25 | 2025-09-26 | Done
| Study SAP FIConfiguration documents | 7 | Research | Study available SAP Financial Accounting (FI) configuration documents for foundational understanding. | ThinhND |  | 2025-09-26 | 2025-09-26 | Done
| Research Config Materials Management, Financial Accounting | 3 | Research | Research general configuration best practices for MM and FI in an SAP environment. | DungNQ |  | 2025-09-28 | 2025-09-28 | Done
| Research and learn about advanced directions | 4 | Research | Explore advanced directions or latest trends related to the project topic | ThinhND |  | 2025-09-29 | 2025-09-29 | Done
| Find out information about Tecomen company | 2 | Research | Find out information about products and prices of Tecomen company | NguyenVC |  | 2025-09-27 | 2025-09-27 | Done
1.3 | BACKGROUND RESEARCH AND ANALYSIS
| Prepare Technical Document Template | 2 |  | Prepare a standardized template for technical documentation to be used throughout the project. | TuNT
| Draw RACI Matrix | 3 | Design | Draw the RACI matrix to clearly define responsibilities (Responsible, Accountable, Consulted, Informed) for all project tasks. | LongHH |  | 2025-09-27 | 2025-09-27 | Done
| Setup Technical Environment | 1 |  | Set up the necessary technical workspace, tools, and access for the project team. | NguyenVC |  | 2025-09-27 | 2025-09-27 | Done
| Kick-off Workshop with stakeholders | 4 |  |  | All team |  | 2025-09-29 | 2025-09-30 | Done
| Meeting with Supervisor & Mentor – Review documents | 5 |  |  | LongHH |  | 2025-10-01 | 2025-10-01 | Done
| Stage 2 – Requirement Gathering & BRD (02/10/2025 – 07/10/2025) | [7 empty] | Done
2.1 | REQUIREMENTS GATHERING & AS-IS ANALYSIS | [7 empty] | Done
| Collect requirements from stakeholders | 6 | Design | Gather business needs, functional expectations, and validation rules from key users and process owners. | TuNT |  | 2025-09-30 | 2025-10-01 | Done
| Draw As-Is diagrams | 4 | Design | Formal documentation of current state processes, including diagrams (e.g., PO–GR–Invoice Flow, Vendor Master Process). | LongHH |  | 2025-10-02 | 2025-10-03 | Done
| Identify and classify pain points & requirements | 3 | Design | Analyze current challenges (Pain Points) and categorize requirements (MANDATORY, DESIRED, FUTURE) | LongHH |  | 2025-10-01 | 2025-10-02 | Done
| Analyze and validate business data samples | 3 |  | Review and cross-reference business data samples (PO, GR note, Invoice) against gathered requirements for feasibility | ThinhND |  | 2025-10-03 | 2025-10-03 | Done
2.2 | TO-BE DESIGN & GAP ANALYSIS |  |  |  | DungNQ
| Perform Gap-Fit analysis | 4 | Research | Compare AS-IS processes against SAP Standard functionality to identify process and system gaps. | NguyenVC |  | 2025-10-04 | 2025-10-04 | Done
| Define and model TO-BE business processes | 5 | Research | Design and diagram the Future State processes within the SAP system environment. | NguyenVC |  | 2025-10-04 | 2025-10-04 | Done
| Identify RICEFW objects and enhancements | 8 | Research | Determine and list all necessary custom developments (Reports, Interfaces, Conversions, Enhancements, Forms, Workflow) to close identified Gaps. | DungNQ |  | 2025-10-04 | 2025-10-05 | Done
| Draft preliminary data migration strategy | 3 | Research | Determine initial data entities and outline the basic approach for data migration. | TuNT |  | 2025-10-05 | 2025-10-05 | Done
2.3 | DOCUMENTATION AND TECHNICAL PREPARATION
| Draft complete Business Requirement Document | 5 |  | Consolidate all requirements, AS-IS, TO-BE processes, and Gap Analysis results into the formal BRD. | ThinhND
| Update the scope of work and custom features | 2 |  | Module in scopes MM, FI/CO, Custom Feature: Excel Upload for Goods Receipt | TuNT |  | 2025-10-05 | 2025-10-06 | Done
| Develop Functional Specification Documents (FSD) | 6 |  | Write and finalize Functional Specifications for all confirmed custom requirements . | LongHH |  | 2025-10-05 | 2025-10-05 | Done
| Align technical architecture & research | 4 |  | Team meeting to finalize technological approach and research necessary technologies for the next stage. | All team |  | 2025-10-05 | 2025-10-05 | Done
| Complete documents to repository & version control | 2 |  | Save all documents (BRD, FSD, Diagrams, Workflows) to the project repository and ensure proper version control | All team |  | 2025-10-05 | 2025-10-06 | Done
Stage 3 –Config (06/10/2025 – 25/10/2025, 20 days)
3.1 | PURCHASING BUSINESS PROCESS | [5 empty] | 2025-10-07 | 2025-10-09
Organization Structure | Company Code | 1 | Master Data | Define company’s financial entity for accounting purposes |  |  |  |  | Done
| Plant | 1 | Master Data | Define plant representing physical or logical location |  |  |  |  | Done
| Assign Plant to Company Code | 1 | Master Data | Link each plant to its controlling company code |  |  |  |  | Done
| Storage Locations | 1 | Master Data | Define storage locations within a plant |  |  |  |  | Done
| Maintain Storage Location | 1 | Master Data | Maintain details and addresses for storage locations |  |  |  |  | Done
| Create Purchasing Group (without Email and Telephone) | 1 | Master Data | Create purchasing groups responsible for specific procurement areas | LongHH |  | 2025-10-07 | 2025-10-09 | Done
| Create Purchasing Organization | 1 | Master Data | Define purchasing organization for procurement activities | LongHH |  | 2025-10-07 | 2025-10-09 | Done
| Assign Purchase Org to Company Code | 1 | Master Data | Assign purchasing organization to company code | LongHH |  | 2025-10-07 | 2025-10-09 | Done
| Assign Purchase Org to Plant | 1 | Master Data | Link purchasing organization to specific plant | LongHH |  | 2025-10-07 | 2025-10-09 | Done
PR | Number range PR | 1 | Master Data | Define number range interval for purchase requisitions |  |  | 2025-10-07 | 2025-10-09 | Done
| PR type | 1 | Master Data | Define document type for purchase requisitions | DungNQ |  | 2025-10-07 | 2025-10-09 | Done
| Edit Characteristic PR | 1 | Standard Config | Configure characteristics for PR classification | DungNQ |  | 2025-10-07 | 2025-10-09 | Done
| Edit Class PR | 1 | Standard Config | Maintain class definitions for PR release strategies |  |  | 2025-10-07 | 2025-10-09 | Done
| Release Groups PR | 2 | Standard Config | Define release groups for purchase requisitions | DungNQ |  | 2025-10-07 | 2025-10-09 | Done
| Release Codes PR | 2 | Standard Config | Define approval codes for PR release process |  |  |  |  | Done
| Release Indicators PR | 2 | Standard Config | Define status indicators for PR release | LongHH |  | 2025-10-08 | 2025-10-09 | Done
| Release Strategies PR | 2 | Standard Config | Configure approval strategy for PRs | LongHH |  | 2025-10-08 | 2025-10-09 | Done
| Workflow For Release Codes PR | 2 | Standard Config | Link PR release codes to workflow process | TuNT |  | 2025-10-10 | 2025-10-11 | Done
| Workflow PR | 3 | Standard Config | Configure workflow for PR approval | TuNT |  | 2025-10-10 | 2025-10-11 | Done
RFQ | Number range RFQ | 1 | Master Data | Define number range interval for RFQs | ThinhND |  | 2025-10-11 | 2025-10-11 | Done
| RFQ type | 1 | Master Data | Define document type for request for quotation | ThinhND |  | 2025-10-11 | 2025-10-11 | Done
PO | Number range PO | 1 | Standard Config | Define number range interval for purchase orders | DungNQ |  | 2025-10-11 | 2025-10-11 | Done
| PO type | 1 | Standard Config | Define document type for purchase orders | DungNQ |  | 2025-10-11 | 2025-10-11 | Done
| Edit Characteristic PO | 2 | Standard Config | Configure characteristics for PO classification | DungNQ |  | 2025-10-11 | 2025-10-11 | Done
| Edit Class PO | 2 | Standard Config | Maintain class definitions for PO release strategies | DungNQ |  | 2025-10-11 | 2025-10-11 | Done
| Release Groups PO | 2 | Standard Config | Define release groups for purchase orders | DungNQ |  | 2025-10-11 | 2025-10-11 | Done
| Release Codes PO | 2 | Standard Config | Define approval codes for PO release process | DungNQ |  | 2025-10-11 | 2025-10-11 | Done
| Release Indicators PO | 2 | Standard Config | Define status indicators for PO release | DungNQ |  | 2025-10-11 | 2025-10-11 | Done
| Release Strategies PO | 2 | Standard Config | Configure approval strategy for POs | DungNQ |  | 2025-10-11 | 2025-10-11 | Done
| Workflow For Release Codes PO | 2 | Standard Config | Link PO release codes to workflow process | DungNQ |  | 2025-10-12 | 2025-10-12 | Done
| Workflow PO | 3 | Standard Config | Configure workflow for PO approval | DungNQ |  | 2025-10-12 | 2025-10-12 | Done
Contract | Create Contract | 2 | Standard Config | Create purchasing contracts for long-term agreements | DungNQ |  | 2025-10-12 | 2025-10-12 | Done
| Approve Contract | 2 | Standard Config | Configure release and approval for purchasing contracts | DungNQ |  | 2025-10-12 | 2025-10-12 | Done
SES | Create SES | 5 | Standard Config | Create service entry sheet for service procurement | DungNQ |  | 2025-10-12 | 2025-10-12 | Done
| Approve SES | 2 | Standard Config | Configure release process for SES approvals | DungNQ |  | 2025-10-12 | 2025-10-12 | Done
3.2 | FINANCAL PROCESS
Invoice | Create invoice | 3 | Standard Config | Record supplier invoice for goods or services received | LongHH |  | 2025-10-13 | 2025-10-13 | Done
Payment | Manual/Auto payment | 2 | Standard Config | Configure payment process for manual and automatic runs | LongHH |  | 2025-10-13 | 2025-10-13 | Done
| Create Condition Table | 2 | Standard Config | Define condition tables for pricing structure | LongHH |  | 2025-10-13 | 2025-10-13 | Done
| Maintain Access Sequence | 2 | Standard Config | Configure access sequence for condition type determination | LongHH |  | 2025-10-13 | 2025-10-13 | Done
| Maintain Condition Type | 2 | Standard Config | Define condition types for pricing and discounts | LongHH |  | 2025-10-13 | 2025-10-14 | Done
| Maintain Calculation Schema | 2 | Standard Config | Define schema to control pricing calculation logic | LongHH |  | 2025-10-13 | 2025-10-14 | Done
| Maintain Schema Group for Vendor | 2 | Standard Config | Group vendors for pricing schema determination | LongHH |  | 2025-10-13 | 2025-10-14 | Done
| Maintain Schema Groups for Purchasing Organizations | 2 | Standard Config | Define schema groups for purchasing organizations | LongHH |  | 2025-10-15 | 2025-10-16 | Done
| Assign Schema Group to Purchasing Organization | 2 | Standard Config | Assign schema group to specific purchasing organization | LongHH |  | 2025-10-15 | 2025-10-16 | Done
| Maintain Schema Determination | 2 | Standard Config | Configure schema determination based on vendor and org | LongHH |  | 2025-10-15 | 2025-10-16 | Done
3.3 | VENDOR |  |  |  | LongHH |  | 2025-10-15 | 2025-10-16
Vendor | Assign Number Range to Vendor Account Groups | 2 | Standard Config | Assign predefined number ranges to vendor account groups | LongHH |  | 2025-10-15 | 2025-10-16 | Done
| Create number ranges for vendors account | 2 | Standard Config | Define number range intervals for vendor master records | LongHH | ThinhND | 2025-10-15 | 2025-10-16 | Done
| Define business partners number ranges | 2 | Standard Config | Create number range intervals for Business Partner master data | ThinhND | LongHH | 2025-10-15 | 2025-10-16 | Done
| Defining BP groups and assigning number ranges | 2 | Standard Config | Define BP grouping categories and link them with number ranges | LongHH | ThinhND | 2025-10-15 | 2025-10-16 | Done
| Assign BP Account group and Supplier group | 2 | Standard Config | Map BP account groups to corresponding supplier account groups | ThinhND | LongHH | 2025-10-15 | 2025-10-16 | Done
Stage 4 - Coding & Testing (17/10/2025 – 13/11/2025, 25 days)
4.1 | W.R.I.C.E.F
| Develop custom : Tool create PR by Excel (C) | 24 | Customize | This tool will enable users to create multiple Purchase Requisitions (PRs) in bulk by uploading an Excel file, which saves time and reduces manual entry errors. Program: ZPG_G1_ZMMC101 | DevTeam |  | 2025-10-17 | 2025-10-23 | Done
| Develop custom : Report list PRs & create RFQ reference by PR (R) | 48 | Customize | From this report, users will have the ability to select PRs and create a Request for Quotation (RFQ) with reference to them, streamlining the procurement and sourcing process. Tcode: ZMMR101 Program: ZPG_G1_ZMMR101 | DevTeam |  | 2025-10-24 | 2025-10-31 | Done
| Develop custom: Send rfq information via email | 20 | Customize | Once created, RFQ is automatically sent to the vendor so they can access and view RFQ information. | DevTeam |  | 2025-11-13 | 2025-11-20 | Done
| Enhance PO Form printed in T-code ME23/ME23N (E, F) | 24 | Customize | Ensure the printed document contains all necessary information and adheres to the company's required format. The print layout (Form) for Purchase Orders (PO) used in transaction code ME23N (Display Purchase Order). Smartform: ZFORM_G1_PO | DevTeam |  | 2025-10-23 | 2025-10-27 | Inprogress
| Reseach & learn BTP,BAS to develop, deploy Fiori application to FLP. | 18 | Research | Focuses on researching and learning SAP Business Technology Platform (BTP) and Business Application Studio (BAS). Request an trial account on SAP BTP for development purpose. Research and practice some projects on BTP. | DevTeam |  | 2025-11-05 | 2025-11-06 | Inprogress |  | Review & request Technical support from mentor
| Develop fiori application allow Vendor access & submit price for Quotations (R,I) | 40 | Customize | This application will provide vendors with a portal to access Requests for Quotation (RFQs) and submit their pricing and proposals directly into the system, automating and accelerating the quotation process. Fiori application: ZGVIF201 - Vendor input price | DevTeam |  | 2025-11-07 | 2025-11-10 | Pending
| Intergate Approval workflow with Microsoft Teams (I,W) | 40 | Research | Integrate the SAP approval workflow with Microsoft Teams. This will allow approvers to receive notifications and approve or reject requests (e.g., PRs or POs) directly within the Microsoft Teams interface, making the approval process faster and more convenient. | DevTeam |  | 2025-11-11 | 2025-11-13 | Pending |  | Review & request Technical support from mentor
4.2 | Document + Testing
| Test tool upload PR - UT | 12 | Test | Conduct UT for custom program ZMMC101 that uploads Purchase Requisitions from Excel. Verify screen layout, file validation rules, ALV display, and PR creation via BAPI. | DungNQ | TuNT | 2025-10-27 | 2025-11-03 | Done
| Test tool upload PR - FT | 12 | Test | Verify that the Excel Upload Tool correctly creates PRi n SAP system with valid data mapping and error handling. | ThinhND |  | 2025-10-27 | 2025-11-03 | Done
| Develop Functional Specification Documents RFQ (FSD) | 5 | Document | Write and finalize Functional Specifications for Report list PRs & create RFQ . | LongHH |  | 2025-11-02 | 2025-11-05 | Done
| Develop Technical Specification Documents PRs (TSD) | 5 | Document | Write Technical Specification document for PR creation tool from Excel | NguyenVC |  | 2025-10-22 | 2025-10-23 | Done
| Develop Technical Specification Documents RFQ (TSD) | 5 | Document | Write Technical Specification document for Report list PRs & create RFQ reference by PR | NguyenVC |  | 2025-11-05 | 2025-11-06 | Done
| Test tool Create RFQ - UT | 12 | Test | Validate that the RFQ Upload Tool (ZMMR101) correctly reads Excel input, performs field-level validation, and displays ALV with correct success/error status before RFQ creation. | DungNQ | TuNT | 2025-11-07 | 2025-11-13 | Done
| Test tool Create RFQ - FT | 12 | Test | Verify that the RFQ Upload Tool (ZMMR101) correctly uploads Excel data to create RFQs, validates input, and logs errors or successes accurately. | ThinhND |  | 2025-11-07 | 2025-11-13 | Done
| Develop UM Documents PR | 10 | Document | Write and finalize UM Documents for Report list PRs . | LongHH | DungNQ | 2025-11-07 | 2025-11-12 | Done
4.3 | Launch Fiori
| Create Catalog Tool Upload PRs ZMMC101 | 4 | Design | Create Catalog Tool Upload PRs – Function test to verify catalog data upload process for Purchase Requisitions. | ThinhND |  | 2025-11-09 | 2025-11-09 | Done
| Create Group Tool Upload PRs ZMMC101 | 5 | Design | Create Group Tool Upload PRs – Function test to verify group creation and PR upload integration process. | ThinhND |  | 2025-11-09 | 2025-11-09 | Done
| Create Semantics Object ZMMC101 | 2 | Design | Create Semantics Object Tool Report PRs | ThinhND |  | 2025-11-10 | 2025-11-10 | Done
| Create Semantics Object ZMMR101 | 2 | Design | Create Semantics Object Create RFQ | NguyenVC |  | 2025-11-10 | 2025-11-10 | Done
| Create Catalog FMMR101 | 2 | Design | Create Catalog Tool Report PRs and Create RFQ | NguyenVC |  | 2025-11-11 | 2025-11-11 | Done
| Create Group Fiori launchpad ZG1_FA25 | 2 | Design | Create Group Fiori launchpad Tool Report PRs and Create RFQ | NguyenVC |  | 2025-11-12 | 2025-11-12 | Done
Stage 5 Document and Overview (14/11/2025 – 21/11/2025, 17 days)
5.1 | Document
| Prepare Report 4: Business Blueprint & SDS | 2 |  |  | LongHH |  | 2025-11-14 | 2025-11-14 | Pending
| Update UC Specification: Goods Receipt & Vendor Management | 2 |  |  | DungNQ |  | 2025-11-14 | 2025-11-14 | Pending
| Prepare Report 5: Test Documentation | 2 |  |  | LongHH |  | 2025-11-14 | 2025-11-14 | Pending
5.2 | Design | 2 | [6 empty] | Pending
| Update SAP Process Flow (GR & Vendor Invoice) | 2 |  |  | DungNQ |  | 2025-11-01 | 2025-11-01 | Pending
| Update Screen Mock-ups (Fiori: GR, Vendor Master) | 2 |  |  | DungNQ |  | 2025-11-02 | 2025-11-02 | Pending
5.3 | Coding/Configuration | [7 empty] | Pending
| Develop Custom Reports | 2 |  |  | ThinhND |  | 2025-11-01 | 2025-11-02 | Pending
| Develop Upload Excel Function (GR) | 2 |  |  | NguyenVC |  | 2025-11-02 | 2025-11-03 | Pending
| Develop Integration APIs | 2 |  |  | ThinhND |  | 2025-11-03 | 2025-12-03 | Pending
| Vendor Contract Management Functions | 2 |  |  | ThinhND |  | 2025-11-03 | 2025-11-04 | Pending
| Enhance Control Functions & Frontend | 2 |  |  | NguyenVC |  | 2025-11-04 | 2025-11-04 | Pending
| Develop Custom Logs | 2 |  |  | ThinhND |  | 2025-11-04 | 2025-12-05 | Pending
5.4 | Testing | [7 empty] | Pending
| Create PO file for data and testing | 2 | Test | Create a sample PO file to generate test data for verifying and validating the ZMMC003 functionality. | TuNT |  | 2025-11-16 | 2025-11-18 | Done
| Upload sample PO file to execute and verify the upload process in ZMMC003. | 2 | Test | Provides the necessary test execution to confirm that the system correctly processes and interprets the uploaded PO file within the ZMMC003 program | TuNT
| Execute Test Cases (GR & Vendor Invoice) | 2 |  |  | ThinhND |  | 2025-11-05 | 2025-11-05 | Pending
| Validate Upload Excel Function | 2 |  |  | TuNT |  | 2025-11-05 | 2025-11-05 | Pending
5.5 | Review & Planning | [7 empty] | Pending
| Review Process Flow & Mock-ups | 2 |  |  | All team |  | 2025-11-05 | 2025-11-05 | Pending
| Approve Report 4 & 5 | 2 |  |  | All team |  | 2025-11-05 | 2025-11-05 | Pending
| Stage 6 – Finalization & Deployment (08/12/2025 – 14/12/2025) | [7 empty] | Pending
6.1 | Document | [5 empty] | 2025-12-08 | 2025-12-10 | Pending
| Finalize SAP Design Document | 2 |  |  | LongHH | DungNQ | 2025-12-08 | 2025-12-09 | Pending
| Finalize Test Documentation | 2 |  |  | DungNQ | LongHH | 2025-12-09 | 2025-12-10 | Pending
| Finalize User Guides (Procurement & Finance) | 2 |  |  | LongHH | DungNQ | 2025-12-09 | 2025-12-10 | Pending
| Prepare Project Closure Report | 2 |  |  | DungNQ | LongHH | 2025-12-10 | 2025-12-10 | Pending
6.2 | Coding | [5 empty] | 2025-12-09 | 2025-12-11 | Pending
| Fix Bugs from UAT | 4 |  |  | NguyenVC |  | 2025-12-09 | 2025-12-10 | Pending
| Optimize System Performance | 4 |  |  | TuNT |  | 2025-12-10 | 2025-12-11 | Pending
| Finalize Enhancements (Excel Upload, Notifications, Vendor Reports) | 4 |  |  | ThinhND |  | 2025-12-11 | 2025-12-11 | Pending
6.3 | Testing | [5 empty] | 2025-12-11 | 2025-12-13 | Pending
| Final Unit Tests | 2 |  |  | ThinhND |  | 2025-12-11 | 2025-12-11 | Pending
| Final Integration Tests (MM–FI) | 2 |  |  | NguyenVC |  | 2025-12-12 | 2025-12-12 | Pending
| Final System Tests | 2 |  |  | TuNT |  | 2025-12-12 | 2025-12-13 | Pending
| Final Acceptance Tests | 2 |  |  | ThinhND |  | 2025-12-13 | 2025-12-13 | Pending
| Bug Fixing & Retesting | 2 |  |  | NguyenVC |  | 2025-12-13 | 2025-12-13 | Pending
6.4 | Deployment | [5 empty] | 2025-12-13 | 2025-12-13 | Pending
| Deploy Backend (SAP Core Config + ZTables) | 2 |  |  | ThinhND |  | 2025-12-13 | 2025-12-13 | Pending
| Deploy Frontend (SAP Fiori Apps) | 2 |  |  | TuNT |  | 2025-12-13 | 2025-12-13 | Pending
6.5 | Final Review | [5 empty] | 2025-12-14 | 2025-12-14 | Pending
| Final Project Review & Sign-off | 2 |  |  | All team |  | 2025-12-14 | 2025-12-14 | Pending